## Insight Inspections Worksheet
Address | 17 South Fenwick Street, Arlington, VA
Date | 2025-05-10
Client | Christina Gordon
Agent | Polly Zephyr
Order # | 1442848882
# | Type | Category | Component | Issue | Location | Recommendation | Resource | Photo 01 | Photo 02 | Photo 03 | Photo 04 | Photo 05 | Photo 06 | Photo 07 | Photo 08 | Photo 09 | Photo 10 | Photo 11 | Photo 12
1 | Safety/Mitigate | HVAC | Heating System 2 | The heating system is inoperative. | Attic | Engage an HVAC contractor to evaluate and to make repairs, as required. | HVAC contractor | Photo 01: Photo; Photo 02: Photo
2 | Safety/Mitigate | Interior | Interior Floors | The carpet is damaged or deteriorated. | Basement | Secure or replace the carpet. | Flooring contractor | Photo 01: Photo
3 | Repair/Fix | Exterior | Exterior Trim | The trim is deteriorated. | Multiple Locations | Replace the trim and repair any damage which may be revealed. | Siding contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
4 | Repair/Fix | Water Control | Grading | There are voids in the grading near the foundation. | Left Side | Regrade to divert surface water away from foundation; grading should be sloped at 1”/foot up to 6’ from the house. | Landscaping contractor | Photo 01: Photo
5 | Repair/Fix | Water Control | Gutters/Downspouts | The gutters/downspouts are filled with debris. | Left Side | Clean the gutters. | Gutters contractor | Photo 01: Photo
6 | Repair/Fix | Insulation and Ventilation | Exhaust Ventilation | The exterior hood is blocked. | Rear | Clear the hood. | Experienced professional | Photo 01: Photo
7 | Repair/Fix | Electrical | Branch Circuits | The wiring routes through the adjacent service panel | Basement | Engage and electrical contractor to make repairs,as required | Electrical contractor | Photo 01: Photo; Photo 02: Photo
8 | Repair/Fix | Electrical | Branch Circuits | The conduit’s protective end bushing is missing. | Basement | Engage an electrical contractor to make repairs, as required. | Electrical contractor | Photo 01: Photo
9 | Repair/Fix | HVAC | Heating System 1 | The furnace vent line leaks | Utility Room | Engage an HVAC contractor to make repairs, as required | HVAC contractor | Photo 01: Photo
10 | Repair/Fix | Plumbing | Water Heater | The water temperature at fixtures is excessively high. | Multiple Locations | Reduce the temperature at the water heater. | Experienced professional | Photo 01: Photo
11 | Maintain | Exterior | Driveway | There is a gap between the driveway and the building. | Left Side | Fill and seal the gap. | Driveway contractor | Photo 01: Photo
12 | Maintain | Exterior | Exterior Walls | There are hairline cracks in the siding | Multiple Locations | Seal the cracks;repair or replace the siding, as required | Siding contractor | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo
13 | Maintain | Exterior | Exterior Walls | There are gaps around utility penetrations. | Right Side | Seal around the penetrations. | Experienced professional | Photo 01: Photo
14 | Maintain | Exterior | Exterior Trim | The caulk at the trim is missing or deteriorated. | Multiple Locations | Caulk the trim, prime and paint. | Siding contractor | Photo 01: Photo
15 | Maintain | Exterior | Exterior Trim | The paint is peeling, blistering, or deteriorating. | Multiple Locations | Replace the trim and repair any damage which may be revealed. | Experienced professional | Photo 01: Photo
16 | Maintain | Exterior | Exterior Doors | The threshold below the door isn’t sealed. | Basement | Seal the threshold. | Experienced professional | Photo 01: Photo
17 | Maintain | Exterior | Patio | There is erosion at the edges of the patio. | Right Side | Repair the patio and address any runoff concerns to prevent further erosion. | Experienced professional | Photo 01: Photo; Photo 02: Photo
18 | Maintain | Exterior | Patio | There is a gap between the patio and the foundation. | Front | Fill and seal the gap. | Patio contractor | Photo 01: Photo
19 | Maintain | Fuel Services | Fuel Meter | The gas line is corroded. | Right Side | Engage a plumbing contractor to evaluate the line. | Plumbing contractor | Photo 01: Photo
20 | Maintain | Structure | Floor Structure | There are minor cracks in the floor slab. | Basement | Monitor and engage a structural contractor to evaluate and to make repairs, as required. | Structural contractor | Photo 01: Photo; Photo 02: Photo
21 | Maintain | HVAC | Heating System 1 | The are adjacent to the air handler is corroded | Utility Room | Engage an HVAC contractor to evaluate and make repairs,as required | HVAC contractor | Photo 01: Photo
22 | Maintain | HVAC | Cooling System 2 | The suction line insulation is damaged. | Right Side Exterior | Install an exterior-grade pipe insulation on the suction line. | Experienced professional | Photo 01: Photo
23 | Maintain | HVAC | Distribution | The air filter is dirty. | Multiple Locations | Replace the filter. | Experienced professional | Photo 01: Photo; Photo 02: Photo
24 | Maintain | Interior | Countertops | There is deteriorated sealant at the countertop/backsplash junction. | Kitchen | Replace the caulk. | Experienced professional | Photo 01: Photo
25 | Monitor | Structure | Foundation | There is minor cracking in the foundation wall. | Right Side | Repair and seal cracks. | Experienced professional | Photo 01: Photo; Photo 02: Photo; Photo 03: Photo; Photo 04: Photo